School Improvement Plan

This plan is a result of analysis of the strengths, weaknesses and needs of the school.

These have been identified by our own monitoring, assessment and evaluation systems and also by results from the last Ofsted inspection in October 2024 and feedback from the LA.

2026 – 2027

September 2026 – initial plan (Draft)

Quality of Education

| Objective 1: To monitor the changes made in the curriculum last year and embed and adapt the new changes. To ensure consistency across the school. To ensure the quality of teaching and learning is maintained. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Action | Person responsible | Timescale | Budget | Update |
| Topics are mapped across the curriculum to ensure coverage and secure knowledge and understanding. Monitor links and extend where needed Review the Kapow frameworks - Update year group overviews each half term - Learning journeys for each topic – demonstrate how learning is built upon over time and use to support planning and writing accurate and explicit LIs – complete as needed. | SLT / ML Curriculum leaders to monitor own subject areas. | Start 1st half autumn term and review each half term throughout the year. | Kapow schemes purchased. Leadership time - £225 per day agency cover. |  |
| Regular work surveys by the leadership team to monitor quality of work –through the SLT / ML meetings. Staff to complete work surveys / monitor termly within year groups. | SLT and the leadership team | Start autumn 2 – every half term to complete a work survey looking at the overviews, planning and LIs within the children’s work |  |  |
| Curriculum leaders to arrange times for staff (ECTs, new teachers) to observe lessons and model lessons within their classes. | Parul / MLs | To begin Autumn 2 |  |  |
| To embed the geography / history Kapow schemes. To monitor and extend links with other subjects. | SLT | From September |  |  |

| Objective 2: To monitor strategies to develop the children’s reading comprehension and follow up on the strategies Nicole Gurvidi introduced. To maintain the quality of our teaching and learning across the school |  |  |  |  |
| --- | --- | --- | --- | --- |
| Action | Person responsible | Timescale | Budget | Update |
| To target interventions to support identified needs each term. THEP consultant to provide advice and training. Regular meetings half term | Sandra, Nicole | Autumn term onwards | SLA with THEP |  |
| Staff to share good practise with reading comprehension strategies and ideas in staff meetings per term | SLT | Start Autumn 2. Staff meeting each term |  |  |
| Close the 15% gap between boys and girls by monitoring and evaluating book choices, planning and strategies to use. Autumn term data: Reading Y2 gap – 41% ** Writing Y2 gap – 39% ** Reading Y1 gap – 14% Writing Y1 gap – 11% Reading Rec gap – 10% Writing Rec gap – 14% | Spring term gap data: Read yr 2-41% Write yr 2-41% Read yr 1 – 8% Write Yr 1 – 15% Read Rec – 9% Write Rec – 8% | Summer term gap Read yr 2– 33% Write yr 2– 33% Read yr 1– 22% Write yr 1– 19% Read Rec– 13% Write Rec- 13% |  |  |

Personal development

| Objective 1: To monitor Oracy as a learning tool across the curriculum and the impact. To gain the silver oracy award |  |  |  |  |
| --- | --- | --- | --- | --- |
| Action | Person responsible | Timescale | Budget | Update |
| To embed Oracy as a vital learning tool for learning across the curriculum. Nicole Gurvidi to support as needed. Oracy books within KS1 assemblies. Daily oracy sessions in classes – fruit time and end of day. | Sandra | Autumn term onwards |  |  |
| To monitor the impact through learning observations, presentations delivered by children and quality of writing outcomes. | Sandra |  |  |  |
| To gather pupil voice comments each term |  |  |  |  |
| Sandra to attend Oracy Hub meetings and to gather evidence towards silver oracy award – monitor displays, planning opportunities. | Sandra |  |  |  |
| Nicole to attend Maths Hub meetings and to monitor vocabulary / reasoning used within maths sessions. | Nicole |  |  |  |

| Objective 2: To monitor reasoning and problem solving skills in our maths curriculum and the impact. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Action | Person responsible | Timescale | Budget | Update |
| To organise and lead a staff meeting each term(5 big ideas) | Nicole | One staff meeting per term / phase meetings |  |  |
| Book scrutinies every term to monitor progress. Monitor reasoning and problem solving within sessions. | Nicole and SLT | Every term |  |  |
| Pupil Voice and teacher Voice feedback | Nicole / Sandra | Autumn 2 term onwards |  |  |

Behaviour and attitudes

| Objective 1: Increase children’s attendance by 1%. Continue to ensure that all children are punctual in arriving at school. To remind children of healthier ways to come to school – walk, scooter, bike. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Action | Person responsible | Timescale | Budget | Update |
| Displays re: attendance around the school. Emphasise the Traffic light system and how much learning the children will be missing. Prizes for 100% attendance in an academic year. | Catherine | ****** | No additional budget needed. |  |
| Review the action we are taking to improve attendance: Letters out to parents re traffic light system Phones calls if child not in school Half termly meetings with parents whose children are below 90%. Increase number of meetings and start in autumn 2. Follow up on SEN absences. Issue penalty fines where necessary for holidays and for persistent absence. | Catherine / Patricia | Autumn start Autumn whole school – 91.3%. Spring term whole school – 91% Summer term whole school – 92% | Photocopying costs |  |
| System we follow to resolve attendance concerns: - Standard reminders via letters/call / text followed by meeting - Attendance rewards - Record reasons given when parents report absences - Ensure parents understand the impact of poor attendance. - Staff to speak to families during parent conferences re the impact of absences on learning. | Catherine Patricia | Once per term | Photocopying costs for letters. |  |
| The school has been awarded a Gold travel plan this year. To remind children to walk to school or use a scooter for a healthier way to come to school. Link to School Travel Plan. Bling your scooter competition and celebration | Gosia | Once half term through assemblies / class PSHE sessions Newsletter reminders |  |  |

| Objective 2: To evaluate the monitors role – focus on friendships and the relationships between children |  |  |  |  |
| --- | --- | --- | --- | --- |
| Action | Person responsible | Timescale | Budget | Update |
| Develop a whole school ethos of a shared responsibility for keeping the school environment safe, clean and tidy – monitors. KS1 – tidying up/lining up/Friendship Rec – tidying up/coats/lining up Develop games played within the playground. Adults to model. Focus on friendships and including others | SLT Parul to discuss in KS1 assembly and in School Council meeting within the autumn term. | Start autumn term |  |  |
| Through assemblies, circle time and the School Council to develop the children’s sense of community who take pride and responsibility to make the school a happy, safe place to be. | Gosia, Lamia. |  |  |  |
| To ensure the School Council play a part in organising and managing this responsibility. | Lamia |  |  |  |

Leadership and management

| Objective 1: In response to the high number of complex needs children in the school: To meet the terms of reference within the Tower Hamlets specialist classroom initiative in order to continue to meet the needs of the ASD learners To monitor provision and children’s progress at their own pace. |  |  |  |  |
| --- | --- | --- | --- | --- |
| To continue to develop an effective environment and support children who have a diagnosis of autism to succeed within our school provision. - Teaching Room - Continuous provision Room - Sensory room | Parul | Autumn term onwards |  |  |
| To use and develop the established links between staff at a mainstream setting and staff at Phoenix school. To share good practice and implement strategies for children in our setting. | Parul Phoenix Outreach Resource evenings Training days EP training Peer Review |  | None |  |
| For children working at low academic levels, to continue to make academic progress and follow an appropriate curriculum. | Parul |  | None |  |
| For children working at low academic levels, to continue to develop the assessment tool (Phoenix Steps+ Engagement model) to reflect the small steps of progress made and support target setting. | Parul |  |  |  |

| Objective 2: To continue with the working relationships with other schools within THEP cluster |  |  |  |  |
| --- | --- | --- | --- | --- |
| Specialist Class project – Peer Review and moderation of assessments | Parul | Regular 2-week visits |  |  |
| Links to other schools in Tower Hamlets with the Oracy Hub and maths Hub EYFS drop in sessions | Sandra / Nicole | Half termly meetings |  |  |
| THEP cluster of schools – to work together to support each other on specific projects. | Catherine/SLT | Autumn term |  |  |
| Linking with Junior school through projects – transition, medical, shared training, SEND children | Parul / SLT |  |  |  |
| Work with Elizabeth Selby as the other infant school - monitor across year groups. | SLT |  |  |  |

| Objective 3: To support staff well being and empower staff to fulfil their potential |  |  |  |  |
| --- | --- | --- | --- | --- |
| Half termly meetings planned to support staff well being | SLT |  |  |  |
| Optional check in meetings with a member of SLT |  |  |  |  |
|  | SLT |  |  |  |

Ongoing:

- To continue to develop and embed the Learning Journeys and Learning Intentions across the curriculum by reviewing daily practise and provide training for new staff.

- To embed the new Tower Hamlets Oracy Hub strategies into the curriculum. The school has been awarded a bronze award. This year we will be working towards achieving a silver award. Oracy strategies to be uniform across the school and displayed clearly within the classroom. Assemblies / clubs to have an oracy focus each week. To attend the Oracy membership Hub meetings on a regular basis and work towards the silver award.

- Floor books per class to be used for whole school / focus events – monitor.

- Staff wellbeing – coaching, counselling sessions when needed.

- To continue to engage with parents and monitor and review the impact of the home-school partnership. Complete a survey in September and a pupil survey.